# AKOTOGBO PRODUCTIVE USE OF ENERGY REPORT

# Presented by the

# Productive Use of Energy Team

# of

# Distributed Renewable Energy Enhancement Facility

11th of September 2025

Table of Contents

List of Tables	5

INTRODUCTION	7

ABOUT THE CONTRACTOR	7

PROJECT SITE AND LOCATION	7

Akotogbo Community Overview	7

Geographic Profile	8

Demographic and Socio Economic Profile	8

Mini-Grid Development Project	9

Proposed Capacity	9

Distribution Metrics	9

Micro Stand Alone Energy System Development Project	9

Proposed Capacity	9

Distribution Metrics	9

Energy Substitution for Different Activities	10

Proposed Distance from Processing Sites to Proposed Minigrid	10

METHODOLOGY USED	10

Desktop review, Gap Analysis of Preliminary information and field management activities	10

KEY FINDINGS	11

Income Generating Activities of Agadagba	11

FARMERS	11

AGRO PROCESSING	12

Mobility	14

SME	14

Proposed PUE Equipment	15

ScaleUp Phase	15

FARMING	15

AGRO PROCESSING	15

Mobility	15

SME	16

Pilot Phase	16

FARMING	16

INDIVIDUAL PROCESSING	16

Mobility	17

SME	17

TOTAL ENERGY PROJECTION FOR PUE PILOT MICRO STAND ALONE SYSTEM	17

Detailed Pilot Infrastructure Specifications	18

AgroHub Pilot Infrastructure Specifications	18

Land & Building Layout	18

Cooperative Governance & Operational Arrangement	19

Safety and Compliance	20

Security Features	20

BOQ & Budget	21

Energy Infrastructure	21

Agrohub	21

Sunbread	22

Farming	22

Equipment — Cassava	22

Equipment — Oil palm	22

Mobility	23

SME	23

Others	23

GRAND TOTAL	24

BUDGET FOR OTHER MODELS	24

Financial Model	26

Monthly Revenue	27

Revenue Per User	28

Implementation Plan	28

Conditions for Scaleup	30

Financial & Repayment Metrics (Lease-to-Own triggers)	30

Portfolio On-Time Repayment Rate (core trigger)	30

Portfolio at Risk (PAR) – early delinquency control	30

Collections Coverage of Operating Costs (hub sustainability)	30

Minimum Monthly Collections Threshold (based on your forecast)	30

Reserve Fund Build (prevents breakdown from killing repayments)	30

Operational & Technical Metrics (Proof the hub can actually run)	31

Asset Uptime (processing + charging + SME loads)	31

Energy System Reliability	31

Utilization Threshold (demand proof)	31

Maintenance Compliance (culture trigger)	31

Governance & Accountability Metrics (Prevents elite capture and disputes)	31

Operating Charter Compliance	31

Dispute Resolution Performance	31

Governance Discipline	31

Data & IoT Metrics (Needed for operational proof + investor confidence)	32

Data Completeness	32

Data Integrity (anti-fraud)	32

Market & Value Chain Metrics (Commercial hub readiness)	32

Market Pull / Offtake Proof	32

16) Quality Standard Compliance	32

Inclusion & Social Metrics (Important because your baseline is male-heavy)	32

Participation Targets (minimum inclusion triggers)	32

Practical “Go/No-Go” Scale-Up Gate	33

Monitoring, Evaluation & Reporting (MER)	34

Key Performance Indicators (KPIs)	34

Data Collection and Reporting Tools	34

Feedback Loops	34

Risk Assessment and Mitigation	35

Risks Identified	35

Mitigation Measures	36

Proposed Impact of the PUE on the Community	36

Contribution to the Sustainable Development Goals (SDGs)	37

Challenges And Recommendations	38

Key Challenges	38

Forecasted Implementation Challenge	39

Use of Artificial Intelligence (AI) in Report Development	40

# List of Tables

Table 1: GPS of community	8

Table 2: Demographic and Socio Economic Profile of community	9

Table 3: Energy Substitution for Different Activities	10

Table 4: Distance from Processing Sites to Proposed Minigrid	10

Table 5: Income generating activities	11

Table 6: Gender of interviewed Farmers	11

Table 7: Total Annual Quantity Harvested	12

Table 8: Processing distribution according to Gender	12

Table 9: Processing distribution according to business model	12

Table 10: Machinery Profile of rice	12

Table 11: Machinery profile of Saw mill	12

Table 12: Machinery profile of Multiple grains	13

Table 13: Processing insight	13

Table 14: Mobility interviewed	14

Table 15: SME interviewed	14

Table 16: Farming	15

Table 17: Cassava Processing (1 ton/hr AgroHub Deployment Model) - Scaleup	15

Table 18: il Palm Processing (1 ton/hr AgroHub Deployment Model) - Scaleup	15

Table 19: Mobility Scaleup	16

Table 20: SME - ScaleupPilot Phase	16

Table 21: Farming - Pilot	16

Table 22: Cassava Processing (1 ton/hr AgroHub Deployment Model) - Pilot	16

Table 23: Oil Palm Processing (1 ton/hr AgroHub Deployment Model) - Pilot	17

Table 24: Mobility Pilot	17

Table 25: SME - Pilot Phase	17

Table 26: Total Energy Projection – Pilot	18

Table 27: Pilot Phase Layout – IoT Enabled	19

Table 28: Cooperative Governance & Operational Arrangement	19

Table 29: Safety and Compliance	20

Table 30: Energy Infrastructure Budget	21

Table 31: Civil and Eletrical work budget	21

Table 32: Sunbread budget	22

Table 33: Farming budget	22

Table 34: Cassava equipment	22

Table 35: Oil palm equipment	23

Table 36: Mobility Budget	23

Table 37: SME budget	23

Table 38: Others budget	24

Table 39: Total PUE Pilot budget	24

Table 40: Budget for Individual Model - New Equipment	24

Table 41: Budget for Individual Model - Retrofit	25

Table 42: Budget for Agrohub Model	25

Table 43: Various Implementation models	26

Table 44: Individual model – new Equipment	27

Table 45: Individual model – Retrofit	27

Table 46: Agrohub Model	27

Table 47: Average revenue per user	28

Table 48: Implementation plan	29

Table 49:KPI	34

Table 50: Data Collection and Reporting Tools	34

Table 51: Feedback Loops	34

Table 52: Risks Identified	35

Table 53: Mitigation Measures	36

Table 54: Summary of Projected Outcomes by Year 1	37

Table 55: Project Alignment with SDGs	37

Table 56: Key Challenges and recommendations	39

Table 57: Forecasted Implementation Challenge and recommendation	39

# INTRODUCTION

This study evaluates the needs, viability, profitability, implementation, and long-term sustainability of Productive Use of Energy (PUE) investments in Akotogbo community. The assessment employed a rigorous methodology that combined desktop research, survey design, field-based needs assessments, equipment design, financial modeling, and project management. Key inputs were provided by the Distributed Renewable Energy Enhancement Facility (DREEF), Electrify Microgrid Limited (the mini-grid developer), PUE team and local community leaders. These contributions included technical data, funding support, and facilitation of access to community stakeholders and proposed beneficiaries.

The specific objectives of the study were to:

- Identify potential PUE users, their production/processing capacity, expenses spent on fossil fuel and their power capacity requirements.

- Assess the socio-economic and commercial viability of PUE opportunities

- Propose tailored PUE solutions

- Evaluate users’ willingness to switch from fossil fuels to energy efficient PUE equipments and to connect to the proposed mini-grid for increase productivity.

- Develop an implementation plan for deploying these solutions in the community.

This report provides actionable insights to guide the design and deployment of productive use of energy technologies, strengthen rural enterprises, and align with Nigeria’s broader development priorities, while contributing to the achievement of the Sustainable Development Goals (SDGs).

## ABOUT THE CONTRACTOR

This report is carried out by the PUE team of DREEF with collaboration from other key experts teams namely Technical team, Legal team, Financial team, Procurement team, ESG team.

For more detailed information about the DREEF, kindly click HERE.

# PROJECT SITE AND LOCATION

## Akotogbo Community Overview

Akotogbo, is a coastal community in Irele LGA of Ondo State, it is predominantly inhabited by the Ikale people, with minorities of Ado, Ijaw, and Hausa. Access to Akotogbo community is difficult at the moment of writing this report due to ongoing road construction. The community is accessible by road and sea, linking it to other parts of the state. There is presence of schools, a health centre, hotels, and filling stations, but despite existing grid infrastructure, it has lacked electricity for nearly 20 years, relying instead on generators.

The community has good mobile network coverage with multiple telecom towers. Its economy is largely agrarian, focused on cassava and palm oil. Governance is led by the Larogbo of Akotogbo, Oba Michael Akinfolarin, with peaceful coexistence among other groups’ leaders. The town oversees about 16 smaller farming settlements.

In support of a proposed project, the traditional ruler has already donated land for a powerhouse and the Agro-Hub.

## Geographic Profile

| Community Name | LGA | Coordinates (Lat, Long) | State |
| --- | --- | --- | --- |
| Akotogbo | Irele | 6.384038; 5.045303. | Ondo |

Table 1: GPS of community

## Demographic and Socio Economic Profile

The majority of households rely on farming, trading and processing of cassava to Garri and Pupuru. Agro-processors focuses mostly on cassava and slight oil palm processing, mostly operate in open-air sheds using diesel-powered equipment. Market access is high as Akotogbo has a very popular market that they buy and sell.

| Category | Details |
| --- | --- |
| Topography and Climate | Savannah terrain with a tropical climate during the wet season and temperate conditions during the dry season. |
| Land Use | Primarily agricultural, with residential and trade activities and limited electrification |
| Population Estimates | ~860 people |
| Number of Households | Approximately 200 households |
| Major Ethnic Groups | Yoruba and Ado people |
| Languages Spoken | Predominantly Yoruba, pidgin English |
| Key Economic Activities | Farming, processing, fishing and trading |
| Key Agro Commodities | oil palm, and cassava |
| Processing Methods | Cassava: Manual and mechanical (e.g., grinding); Oil Palm: Predominantly mechanical (digesting, pressing); |
| Number of Agro-Processors | 7 identified processors |
| Farmers' Cooperative | No cooperative |
| Natural Resources | River |
| Environmental Challenges | Flooding |
| Infrastructure | Bad roads, No electricity, sparse water infrastructure |

Table 2: Demographic and Socio Economic Profile of community

## Mini-Grid Development Project

### Proposed Capacity

  - Solar PV: 315.5 kWp

  - Battery Storage: 645 kWh

  - Annual Consumption: 432,847.02 kWh

### Distribution Metrics

Target End Users:

- Residential (90.34%): Households for lighting, fans, charging, televisions, and refrigerators.

- Commercial (7.67%): Enterprises such as shops, tailors, salons, and agro-processors.

- Public (1.75):

- Productive Loads (0.85%): Small-scale industries (e.g., milling, welding) and public

## Micro Stand Alone Energy System Development Project

### Proposed Capacity

  - Solar PV: 50 kWp

  - Battery Storage: 50 kWh

  - Annual Consumption: 32,847.02 kWh

### Distribution Metrics

Target End Users:

- Agricultural Processing (85.0%): Oilpalm and Cassava processing.

- SME (7.5%): Enterprises such as refrigiration and Phone charging.

- Mobility (7.5): Two wheelers

- Productive Loads (0.85%): Small-scale industries (e.g., milling, welding) and public

## Energy Substitution for Different Activities

The mini grid will replace or supplement existing energy sources as outlined below:

| Use Case | Current Energy Source | Replacement |
| --- | --- | --- |
| Household lighting | Kerosene lamps, petrol generators, | Solar electricity |
| Grinding (cassava); Digesting (Oilpalm) | Diesel/petrol engines | PUE machines |
| SME | Small petrol generators | Reliable solar mini-grid power |
| Mobility | Petrol powered two-wheelers | Electric powered two-wheelers |

Table 3: Energy Substitution for Different Activities

## Proposed Distance from Processing Sites to Proposed Minigrid

The table below shows the GPS coordinates of the Proposed Agrohub, Swap station and SME site at Akotogbo community, the coordinates of the proposed minigrid location, and the calculated straight-line distance between them.

| Name of Processor | Site Longitude | Site Latitude | Minigrid Longitude | Minigrid Latitude | Distance (km) |
| --- | --- | --- | --- | --- | --- |
| Agrohub and swap station | 6.384038 | 5.045303 | 6.384038 | 5.045303 | 0.10 |
| Cassava Processor |  |  |  |  |  |
| Oyewumi Adeomo | 6.3846408 | 5.0433827 | 6.384038 | 5.045303 | 0.22 |

Table 4: Distance from Processing Sites to Proposed Minigrid

# METHODOLOGY USED

## Desktop review, Gap Analysis of Preliminary information and field management activities

A desktop review and gap analysis was conducted to establish baseline information on the communities and their mini-grid development prospects. This included assessments of energy demand, household demographics, existing energy sources, environmental and infrastructural factors, financial viability, and regulatory frameworks. Where information was lacking, gaps were identified for follow-up during fieldwork. A detailed description of this process, including survey design, site reconnaissance, data collection methodology, and the field deployment and management activities is provided HERE

# KEY FINDINGS

## Income Generating Activities of Agadagba

| People interviewed | 166 |
| --- | --- |
| Farmer | 100 |
| Agroprocessors | 6 |
| SME | 10 |
| Mobility | 50 |

Table 5: Income generating activities

### FARMERS

Table 6: Gender of interviewed Farmers

| Gender | Male | 32 |
| --- | --- | --- |
|  | Female | - |

| Crop | Farming household | Percentage | Annual Production Interviewed | Estimated Annual Production (100kg bag) Community | Total Area Planted (m2) |
| --- | --- | --- | --- | --- | --- |
| yam | 12 | 7.2 | 511,930 | 1,072,907.19 | 275,000 |
| tomato | 9 | 5.4 | 952 | 1,995.21 | 172,500 |
| sesame | 1 | 0.6 | 48 | 100.60 | 20,000 |
| soyabeans | 17 | 10.2 | 235 | 492.51 | 195,900 |
| millet | 2 | 1.2 | 7 | 13.62 | 51,350 |
| pepper | 2 | 1.2 | 46 | 96.41 | 12,500 |
| maize | 139 | 83.2 | 16,733 | 35,069.16 | 3,187,500 |
| ground nut | 3 | 1.8 | 18 | 37.72 | 7,700 |
| beans | 77 | 46.1 | 1,535 | 3,216.02 | 1,453,875 |
| guineacorn | 18 | 10.8 | 514 | 1,077.25 | 310,000 |
| rice | 52 | 31.1 | 1,749 | 3,665.57 | 753,850 |

Table 7: Total Annual Quantity Harvested

### AGRO PROCESSING

| No of Agroprocessing |  |
| --- | --- |
| Male | 18 |
| Female | 0 |

Table 8: Processing distribution according to Gender

| Crops Processed | Male | Female | cash as a service | goods as a service | purchase raw materials |
| --- | --- | --- | --- | --- | --- |
| maize | 5 | 0 | 4 | 1 | 0 |
| saw mill | 3 | 0 | 3 | 0 | 0 |
| multiple grains | 7 | 0 | 7 | 0 | 0 |
| rice | 3 | 0 | 3 | 0 | 0 |

Table 9: Processing distribution according to business model

| rice | Chaf remover | 15 horse power | 1 |
| --- | --- | --- | --- |
|  | Rice milling machine | 30 HP electric motor machine | 1 |
|  | Rice milling machine | 20 HP electric motor machine | 1 |
|  | Rice distoner | 3 HP electric motor machine | 1 |
|  | Rice distoner machine | 5 HP electric motor machine | 1 |

Table 10: Machinery Profile of rice

| saw mill | Saw miller | 15 horse power | 1 |
| --- | --- | --- | --- |
|  | Saw miller | 15 HP electric motor machine Combined with 15 HP power diesel engine | 1 |
|  | Saw mill | Diesel engine 1115 | 1 |

Table 11: Machinery profile of Saw mill

| Multiple grains | Grinding mill | 15 HP electric motor machine | 2 |
| --- | --- | --- | --- |
|  | Rice mill | 15 HP electric motor machine | 3 |
|  | Rice milling machine | 15 HP electric motor machine | 1 |
|  | Chaf remover | 25 horse power | 1 |
|  | Rice milling machine | 30 HP electric motor machine | 2 |
|  | Rice milller | 15 HP electric motor machine | 1 |
|  | Maize grinding mill | 15 HP electric motor machine | 3 |
|  | Maize grinding mill | 10 HP electric motor machine | 1 |
|  | Grinding machine | 15 horse power | 1 |
|  | Grinding mill | 5 HP electric motor machine | 1 |

Table 12: Machinery profile of Multiple grains

Processing Insights:

- Average output: 17 bags (100 kg/bags) per week in peak season; 11 bags (100 kg/bags) in scarce season.

- Grinding time: ~15–20 minutes per 100kg/bags.

- Diesel use: ~8.5 litres weekly for 17 bags; approx. 442 litres annually.

- Annual production: ~656 bags (100 kg).

#### Oilpalm  Processing (Semi-Mechanised Method)

- Number Interviewed: 1 (1 male)

- Business Model: The processor use "cash-for-service” model

| Crops Processed | Total Quantity Processed (Peak) | Total Quantity Processed (Scarce) | Average Quantity (Peak) | Average Quantity Processed (Scarce) |
| --- | --- | --- | --- | --- |
| maize | 5868 | 1256 | 1174 | 251.2 |
| saw mill | 21800 | 816 | 7267 | 408 |
| multiple grains | 13524 | 2360 | 1932 | 337.1428571 |
| rice | 6880 | 2992 | 2293 | 997.3333333 |

Table 13: Processing insight

- Average output: 2 drums per week in peak season; 1 drum in scarce season.

- Digestion time: ~15 minutes per sack.

- Petrol use: ~2.5litres daily for 3 drums; approx. 130 litres annually.

- Annual production: ~60 drums.

### Mobility

| E-Mobility | 12 |
| --- | --- |
| Okada | 11 |
| Tricycle | 1 |
| Boat | 0 |

Table 14: Mobility interviewed

- Daily Operation hours: 7 hours per day.

### SME

| SME | 18 |
| --- | --- |
| barbershop | 2 |
| Cold Storage/Ice Block Making | 4 |
| Grocery Retail | 2 |
| Phone Charging | 1 |
| Phone Repair | 1 |
| Cain Production | 1 |
| Hairdressing | 0 |
| Welding | 0 |
| Printing/Cybercafé | 2 |
| Carpentary | 1 |
| Tailoring/Fashion | 2 |
| Others | 2 |

Table 15: SME interviewed

# Proposed PUE Equipment

## ScaleUp Phase

### FARMING

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Irrigation system | 122galons/hr | 3 | 1 | Stand alone solar |
| TOTAL |  |  | 3 |  |

Table 16: Farming

### AGRO PROCESSING

#### Cassava Processing (1 ton/hr AgroHub Deployment Model)

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Peeler and washer | 1 ton/hour | 5 | 2 | Micro Stand alone solar |
| Grater | 1 ton/hour | 7.5 | 2 | Micro Stand alone solar |
| Presser | 1 ton/hour | 4 | 2 | Micro Stand alone solar |
| sifter | 1 ton/hour | 3 | 2 | Micro Stand alone solar |
| Milling Machine | 1 ton/hour | 7.5 | 2 | Micro Stand alone solar |
| TOTAL |  | 27 | 54 |  |

Table 17: Cassava Processing (1 ton/hr AgroHub Deployment Model) - Scaleup

#### oilpalm  Processing (Semi-Mechanised Method)

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Thresher | 1 ton/hour | 5 | 2 | Micro Stand alone solar |
| Digester | 1 ton/hour | 7.5 | 2 | Micro Stand alone solar |
| Presser | 1 ton/hour | 4 | 2 | Micro Stand alone solar |
| Cracker | 1 ton/hour | 3 | 2 | Micro Stand alone solar |
| TOTAL |  | 19.5 | 39 |  |

Table 18: il Palm Processing (1 ton/hr AgroHub Deployment Model) - Scaleup

### Mobility

E-Okada Specification:

- Top Speed 80km per hr

- Range 120km

- Power Rating 3skw , Battery 4.3kwh

| E-Mobility Vehicles | Capacity | Quantity | Charging Rate (kW/hr ) | Charging Time (Hours) |
| --- | --- | --- | --- | --- |
| Two Wheelers | 120km full charge | 3 | 1.35 | 3 |
| Three Wheelers | 120km full charge | 2 | 1.35 |  |
| TOTAL |  | 5 | 6.75 |  |

Table 19: Mobility Scaleup

### SME

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Refrigirator | 250l deep chest freezer | 0.3 | 1 | Micro Stand alone solar |
| Phone Charging | 50 boxes | 3 | 1 | Micro Stand alone solar |
| TOTAL |  |  | 3.3 |  |

Table 20: SME - ScaleupPilot Phase

### Pilot Phase

### FARMING

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Irrigation system | 122galons/hr | 3 | 1 | Stand alone solar |
| TOTAL |  |  | 3 |  |

Table 21: Farming - Pilot

### INDIVIDUAL PROCESSING

#### Cassava Processing (1 ton/hr Individual Deployment Model)

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Grater | 1 ton/hour | 7.5 | 1 | Micro Stand alone solar |
| Presser | 1 ton/hour | 4 | 1 | Micro Stand alone solar |
| TOTAL |  |  | 11.5 |  |

Table 22: Cassava Processing (1 ton/hr AgroHub Deployment Model) - Pilot

#### oilpalm  Processing (Semi-Mechanised Method)

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Digester | 1 ton/hour | 7.5 | 1 | Micro Stand alone solar |
| Presser | 1 ton/hour | 4 | 1 | Micro Stand alone solar |
| TOTAL |  |  | 11.5 |  |

Table 23: Oil Palm Processing (1 ton/hr AgroHub Deployment Model) - Pilot

### Mobility

E-Okada Specification:

- Top Speed 80km per hr

- Range 120km

- Power Rating 3skw , Battery 4.3kwh

| E-Mobility Vehicles | Capacity | Quantity | Charging Rate (kW/hr ) | Charging Time (Hours) |
| --- | --- | --- | --- | --- |
| Two Wheelers | 120km full charge | 3 | 1.35 | 3 |
| Three Wheelers | 120km full charge | 0 |  |  |
| TOTAL |  | 3 | 4.05 |  |

Table 24: Mobility Pilot

### SME

| Machine | Capacity | Power rating (kW/hr) | Quantity | Energy Source |
| --- | --- | --- | --- | --- |
| Refrigirator | 250l deep chest freezer | 0.3 | 1 | Micro Stand alone solar |
| Phone Charging | 50 boxes | 3 | 1 | Micro Stand alone solar |
| TOTAL |  |  | 3.3 |  |

Table 25: SME - Pilot Phase

## TOTAL ENERGY PROJECTION FOR PUE PILOT MICRO STAND ALONE SYSTEM

| ITEM | kW/hr | 6 hour day work |
| --- | --- | --- |
| Cassava | 11.5 | 69 |
| Oil palm | 11.5 | 69 |
| Mobility | 4.05 | 24.3 |
| SME | 3.3 | 19.8 |
| TOTAL | 27.05 | 182.1 |

Table 26: Total Energy Projection – Pilot

# Detailed Pilot Infrastructure Specifications

### AgroHub Pilot Infrastructure Specifications

Each AgroHub functions as a centralized processing facility equipped with electric-powered machinery tailored to the specific crop value chains (oil palm and cassava). The hubs will be:

- Owned by the SPV

- Managed by the cooperative

- Powered by a stand-alone system

- Modular, allowing expansion to accommodate additional machines or processing lines during scale-up phases.

### Land & Building Layout

- Total Land Area One plot = 15m x 30m = 450m2

Sunbread size:

- External Dimensions – 10ft by 10ft container (Outside)

  - Length: 3.03 m

  - Width: 3.04 m

  - Height: 2.59 m

- Internal Dimensions (Inside)

  - Length: 2.90 m

  - Width: 2.90 m

  - Height: 2.39 m

- Floor Area (Inside)

  - 2.9 m×2.9 m≈8.41 m2

Panel Land Size

- Half plot of land: 15m x 15m = 225m2

Agrohub

- Pilot Hub Facility: 3.03m x 3.03m

#### Pilot Phase – Machine Layout & IoT Integration

| Room / Area | Dimension (m) | Area (m²) | Notes / IoT Deployment |
| --- | --- | --- | --- |
| Cassava Graters (1 ton/hr) | 0.7m x 1.5m | 1.05 | Power: 5.5 kW; IoT: RPM, vibration, energy, temp sensors; mounted near motor/hopper. |
| Cassava Presser (1 ton/hr) | 0.8m × 1.5m | 1.2 | Power: 3.5 kW; IoT: throughput, motor temperature, load sensors. |

Table 27: Pilot Phase Layout – IoT Enabled

- Structural Features: Reinforced concrete slab (150–250 mm depending on wet zone), oil-resistant epoxy flooring, graded to drains with oil interceptors, silt traps, and stainless-steel piping.

- Roof: Steel truss with long-span metal sheeting, insulation, and ridge vents for heat and humidity removal.

- Electrical: 3-phase distribution rated ≥ 30 kW with surge protection, per-machine breakers, emergency stop buttons, and IoT energy meters.

- Access & Vehicle Movement: Loading bay 8 m × 3 m for trucks and trailers.

### Cooperative Governance & Operational Arrangement

| Structure | Description |
| --- | --- |
| Cooperative Ownership | Registered multipurpose cooperative owns the AgroHub asset |
| Management Committee | 5-person committee: Chair, Secretary, Treasurer, O&M Rep, Machine Operator Supervisor |
| Usage Fee System | Pay-per-use and revenue-share model (₦/kg and % per batch) |
| Revenue Use | Split between Lease repayment, maintenance fund, cooperative savings, machine operator salaries |
| Operation Hours | 8am – 6pm daily (with booking slots to avoid congestion) |
| Record-Keeping | Daily usage logs, financial records, machine servicing checklist |
| Dispute Resolution | Bylaws + local mediation structure for cooperative members |

Table 28: Cooperative Governance & Operational Arrangement

### Safety and Compliance

| Aspect | Implementation |
| --- | --- |
| Fire Safety | 1 fire extinguishers + 1 fire blanket + sand bucket per hub |
| Machine Safety | Emergency stop buttons, operator training, use of gloves & PPE |
| Electrical Safety | Grounding of machines, surge protectors, ELCBs, visible warning signs |
| Public Health | Regular cleaning, pest-proofing, first aid kit on site |
| Noise Control | Machines installed with dampeners; zoning of quiet vs. loud areas |

Table 29: Safety and Compliance

### Security Features

- Fenced Compound (block wall or wire mesh)

- Night Security Personnel (optional)

- Solar-powered floodlights

- Inventory Ledger for Inputs and Outputs

Figure 1: Agrohub station

# BOQ & Budget

The Bill of Quantity is for the Agrohub model, the BOQ and budgets for other models are available in the financial model worksheet as stated HERE

The breakdown of the budget is listed below

## Energy Infrastructure

| Item | Details | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Metal beam | 10ft metal Container | 1 | 1,800,000 | 1,800,000 |
| Bolt and Screw | 10ft metal Container | 1 | 1,800,000 | 1,800,000 |
| Panel | 30 square foot monochrome | 40 | 150,000 | 6,000,000 |
| Inverter | 20kW inverter system | 2 | 1,500,000 | 3,000,000 |
| Battery | 5kW Lithium ion battery | 8 | 1,500,000 | 12,000,000 |
| Electrical wiring |  |  | 500,000 | 500,000 |

Table 30: Energy Infrastructure Budget

## Agrohub

| Item | Details | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Support and Roofing Beam | 5m metal Container | 25 | 50,000 | 1,250,000 |
| 3-phase distribution board & breakers | For heavy equipment | 1 | 500,000 | 500,000 |
| Roof | Corragated metal sheets | 20 | 50,000 | 1,000,000 |
| Electrical wiring | Copper | 1 | 500,000 | 500,000 |
| Total cost |  |  |  | 3,250,000 |

Table 31: Civil and Eletrical work budget

## Sunbread

| Item | Details | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Metal beam | 10ft metal Container | 1 | 1,800,000 | 1,800,000 |
| Concrete floor slab | 200 mm reinforced, epoxy | 1 | 200,000 | 200,000 |
| Roof extractor | Long span + wood | 1 | 300,000 | 300,000 |
| 3-phase distribution board & breakers | For heavy equipment | 1 | 500,000 | 500,000 |
| Electrical wiring | Copper | 1 | 500,000 | 500,000 |

Table 32: Sunbread budget

## Farming

| Machine | Capacity | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Irrigation system | 122galons/hr | 5 | 1,300,000 | 6,500,000 |
| TOTAL |  |  |  | 6,500,000 |

Table 33: Farming budget

Equipment — Cassava

| Cassava |  |  | NEW |  | RET |  |
| --- | --- | --- | --- | --- | --- | --- |
| Machine | Capacity | Quantity | Unit Price | Total Price | Unit Price | Total Price |
| Grater | 1 ton/hour | 1 | 5,500,000 | 5,500,000 | 2,000,000 | 2,000,000 |
| Presser | 1 ton/hour | 1 | 4,000,000 | 4,000,000 | 4,000,000 | 4,000,000 |

Table 34: Cassava equipment

Equipment — Oil palm

| Oil palm |  |  | NEW |  | RET |  |
| --- | --- | --- | --- | --- | --- | --- |
| Machine | Capacity | Quantity | Unit Price | Total Price | Unit Price | Total Price |
| Digester | 1 ton/hour | 1 | 4,500,000 | 4,500,000 | 1,500,000 | 1,500,000 |
| Presser | 1 ton/hour | 1 | 4,250,000 | 4,250,000 | 4,250,000 | 4,250,000 |
| TOTAL |  |  |  | 8,750,000 |  | 5,750,000 |

Table 35: Oil palm equipment

## Mobility

| E-Mobility Vehicles | Capacity | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Two Wheelers | 120km full charge | 3 | 1,300,000 | 3,900,000 |
| Three Wheelers | 120km full charge | 0 | 3,000,000 | - |
| Extra Battery | 120km full charge | 3 | 1,000,000 | 3,000,000 |
| TOTAL |  |  |  | 6,900,000 |

Table 36: Mobility Budget

## SME

| Machine | Capacity | Quantity | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Refrigirator | 250l deep chest freezer | 1 | 4,500,000 | 1,000,000 |
| Phone Charging | 50 boxes | 1 | 4,250,000 | 150,000 |
| TOTAL |  |  |  | 1,150,000 |

Table 37: SME budget

## Others

| S/N |  | Item | Qty | Unit Cost (₦) | Total (₦) |
| --- | --- | --- | --- | --- | --- |
| 1 | Farming | Transportation & Logistics | 5 | 60,000 | 300,000 |
|  |  | Installation, Testing & Commissioning | 5 | 40,000 | 200,000 |
| 2 | Processing Equipment Cassava | Transportation & Logistics | 1 | 500,000 | 500,000 |
|  |  | Installation, Testing & Commissioning | 1 | 300,000 | 300,000 |
| 3 | Processing Equipment Oil palm | Transportation & Logistics | 1 | 500,000 | 500,000 |
|  |  | Installation, Testing & Commissioning | 1 | 300,000 | 300,000 |
| 4 | Mobility station | Transportation & Logistics | 3 | 200,000 | 600,000 |
|  | Battery | Transportation & Logistics | 3 | 100,000 | 300,000 |
| 5 | SME | Transportation & Logistics | 1 | 300,000 | 300,000 |
| 6 | Insurance | Machines, mobility asset | 2% | 32,800,000 | 656,000 |
| 7 | SPV Engagement | Project Management Fees | 1 | 1,000,000 | 1,000,000 |
|  | TOTAL |  |  |  | 4,456,000 |

Table 38: Others budget

## GRAND TOTAL

| S/N | ITEM | PRICE (₦) |
| --- | --- | --- |
| 1 | Farming Equipment | 6,500,000 |
| 2 | Processing Equipment Cassava | 9,500,000 |
| 3 | Processing Equipment Oil palm | 8,750,000 |
| 4 | Mobility | 6,900,000 |
| 5 | SME | 1,150,000 |
| 6 | Others | 4,456,000 |
|  | TOTAL | 30,756,000 |

Table 39: Total PUE Pilot budget

## BUDGET FOR OTHER MODELS

| Individual Model - New Equipment | Farming Equipment | 5 | 24 | 70,995 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 260,467 |
|  | Processing Equipment Oil palm | 1 | 48 | 241,501 |
|  | Mobility | 3 | 30 | 105,367 |
|  | SME | 1 | 30 | 58,762 |

Table 40: Budget for Individual Model - New Equipment

| Individual Model - Retrofit | Farming Equipment | 5 | 24 | 71,381 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 172,893 |
|  | Processing Equipment Oil palm | 1 | 48 | 166,537 |
|  | Mobility | 3 | 30 | 105,939 |
|  | SME | 1 | 30 | 59,081 |

Table 41: Budget for Individual Model - Retrofit

| Agrohub Model | Farming Equipment | 5 | 24 | 84,475 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 422,757 |
|  | Processing Equipment Oil palm | 1 | 48 | 400,190 |
|  | Mobility | 3 | 30 | 125,372 |
|  | SME | 1 | 30 | 253,156 |

Table 42: Budget for Agrohub Model

# Financial Model

For the financial model for the deployment of PUE in Akotogbo community, several models were tested to get the best fit which will ensure affordability while also providing the appropriate productive use of equipment technology for this pilot phase of deployment. The various models are stated below

| Business Model | Explanation |
| --- | --- |
| Individual Model - New Equipment | Under this model, beneficiaries lease newly procured equipment individually on a lease-to-own basis. Each beneficiary is solely responsible for repayment and eventual ownership of the equipment. |
| Individual Model - Retrofit | In this model, existing beneficiary equipment powered by fossil fuels is retrofitted to electric-powered systems. Beneficiaries pay for the upgrade in installments over the agreed loan repayment period. |
| Agrohub Model | An agricultural hub is established within the community, equipped with shared agro-processing machinery. Beneficiaries collectively lease and manage the equipment as a cooperative, operating under a lease-to-own arrangement. |
| Hybrid Model - New Equipment | An agricultural hub is introduced to the community and shared by two distinct beneficiary sectors, each with a unique payment structure: Farmer Cooperatives: Lease the new Agrohub equipment collectively on a lease-to-own basis. Agroprocessors (Individuals): Lease new equipment individually on a lease-to-own basis. |
| Hybrid Model - New Equipment + Retrofit | An agricultural hub is presented to the community and jointly used by two sectors with different equipment structures and payment terms: Farmer Cooperatives: Lease new Agrohub equipment collectively on a lease-to-own basis. Agroprocessors (Individuals): Have their existing fossil-fuel equipment retrofitted to electric-powered systems and pay for the upgrade over the loan repayment period. |
| Agrohub Model + Grant | This follows the Agrohub Model, but in this case, a grant covers the cost of constructing the Agrohub structure, reducing the financial burden on beneficiaries. |
| Hybrid Model - New Equipment + Grant | This follows the Hybrid Model (New Equipment) framework. However, a grant covers the cost of the Agrohub structure, while beneficiaries maintain lease-to-own payment for the equipment. |
| Hybrid Model - New Equipment + Retrofit + Grant | This follows the Hybrid Model (New Equipment + Retrofit) structure, but with a grant covering the cost of the Agrohub structure, ensuring affordability and sustainability for both cooperatives and individual agroprocessors. |

Table 43: Various Implementation models

### Monthly Revenue

| Individual Model - New Equipment | Farming Equipment | 5 | 24 | 70,995 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 260,467 |
|  | Processing Equipment Oil palm | 1 | 48 | 241,501 |
|  | Mobility | 3 | 30 | 105,367 |
|  | SME | 1 | 30 | 58,762 |

Table 44: Individual model – new Equipment

| Individual Model - Retrofit | Farming Equipment | 5 | 24 | 71,381 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 172,893 |
|  | Processing Equipment Oil palm | 1 | 48 | 166,537 |
|  | Mobility | 3 | 30 | 105,939 |
|  | SME | 1 | 30 | 59,081 |

Table 45: Individual model – Retrofit

| Agrohub Model | Farming Equipment | 5 | 24 | 84,475 |
| --- | --- | --- | --- | --- |
|  | Processing Equipment Cassava | 1 | 48 | 422,757 |
|  | Processing Equipment Oil palm | 1 | 48 | 400,190 |
|  | Mobility | 3 | 30 | 125,372 |
|  | SME | 1 | 30 | 253,156 |

Table 46: Agrohub Model

# Revenue Per User

Here is the Projected Revenue per user for the Minigrid and the various contribution of each action point as.

| Akotogbo | Effective Daily Demand (kWh) | Effective Annual Demand (kWh) | No of Beneficiaries | Average kWh Tariff | Daily Revenue per Category (#/kWh) | Daily Average Revenue (#/kWh) |
| --- | --- | --- | --- | --- | --- | --- |
| Residential | 478.46 | 174,637.90 | 1,085 | 316.210 | 151,293.84 | 139.44 |
| Commercial | 385.88 | 140,846.20 | 92 | 316.210 | 122,019.11 | 1,326.29 |
| Public | 43.9 | 16,023.50 | 21 | 316.210 | 13,881.62 | 661.03 |
| Productive - Individual | 279 | 101,835.00 | 5 | 316.210 | 88,222.59 | 17,644.52 |
| Productive - Agrohub | 153 | 55,845.00 | 5 | 316.210 | 48,380.13 | 9,676.03 |
| Productive - Hybrid | 333 | 121,545.00 | 5 | 316.210 | 105,297.93 | 21,059.59 |

Table 47: Average revenue per user

# Implementation Plan

The implementation for the Akotogbo PUE initiative will take a minimum of 21 weeks (5 months and 1 week) from SPV selection to PUE installation, testing and commissioning . The PUE implementation for the individual deployment model will follow the process below

| S/N | Title | Responsibility | Duration | Timeline |
| --- | --- | --- | --- | --- |
| 1 | SPV selection | Procurement, PUE team | 2 weeks | Week 1 - 2 |
| 2 | Contract Signing | Legal and PUE team | 2 weeks | Week 3 - 4 |
| 3 | Land Engagement with Community | SPV, Minigrid Developer and PUE team | 2 weeks | Week 4-5 |
| 4 | Project Design | Minigrid developer, SPV, OEM, IOT, Civil engineer and PUE team | 2 weeks | week 6-7 |
| 5 | Submission of Budgets | SPV, procurement and PUE team | 1 week | Week 8 |
| 6 | First Payment Made | SPV, Procurement team, PUE team | 2 weeks | Week 9-10 |
| 7 | Account Setup | SPV, Funder firm | 2 weeks | Week 11-12 |
| 8 | Mobilization | SPV and PUE team | 6 weeks | week 13 - 19 |
| 9 | Transportation, Installation and Commisioning | SPV and PUE team | 2 weeks | Week 20-21 |
| 10 | Monitoring and Evaluation | SPV, Financial team and PUE team |  | Week 25 |
|  |  | SPV , DI team and PUE team | Every Quarter |  |

Table 48: Implementation plan

For more information on the PUE implementation Plan, kindly click HERE

# Conditions for Scaleup

Below are the key metrics (KPIs) the community must attain before we “activate” the move from Pilot to Scale-up.

## Financial & Repayment Metrics (Lease-to-Own triggers)

### Portfolio On-Time Repayment Rate (core trigger)

- Target: ≥ 95% on-time repayment for 3 consecutive months

- Definition: % of expected monthly repayments received by due date

- Why it matters: proves discipline + bankability

### Portfolio at Risk (PAR) – early delinquency control

- PAR 30 (payments 30+ days late): Target ≤ 5%

- PAR 60: Target ≤ 2%

- Why it matters: if PAR rises during pilot, scaling multiplies defaults.

### Collections Coverage of Operating Costs (hub sustainability)

- Target: Collections cover 100% of:

  - operators’ wages

  - routine maintenance/spares

  - insurance allocations

  - admin/collections costs

- Threshold: OPEX Coverage Ratio ≥ 1.0 for 3 straight months

### Minimum Monthly Collections Threshold (based on your forecast)

Assuming “Amount (monthly)” is per unit and “Quantity” is the number of units/beneficiaries, the expected total monthly inflow is:

- Individual Model – New equipment: ₦1,231,806/month

- Individual Model – Retrofit: ₦1,073,233/month

- Agrohub Model: ₦1,874,594/month

Scale-up trigger rule (simple and defendable):

- Achieve ≥ 90% of expected monthly inflow for 3 consecutive months, i.e.

  - New equipment: ≥ ₦1,108,625/month

  - Retrofit: ≥ ₦965,910/month

  - Agrohub: ≥ ₦1,687,135/month

### Reserve Fund Build (prevents breakdown from killing repayments)

- Target: Maintain a Maintenance & Replacement Reserve equal to:

  - ≥ 2 months of routine O&M cost or

  - ≥ 5% of monthly collections, whichever is higher

  - Evidence: separate wallet/account + monthly statement

## Operational & Technical Metrics (Proof the hub can actually run)

### Asset Uptime (processing + charging + SME loads)

- Target: ≥ 90–95% uptime during planned operational hours

- Evidence: IoT runtime logs + operator downtime register

### Energy System Reliability

- Target: ≥ 95% availability of the modular solar system during operating window

- Evidence: inverter logs, battery cycles, fault logs

### Utilization Threshold (demand proof)

Scale only when there is clear “pull” from users:

- Processing utilization target: ≥ 60% of available processing hours booked/used for 8 consecutive weeks

- Or: consistent waiting list (unserved demand) for ≥ 20% of available slots weekly

### Maintenance Compliance (culture trigger)

- Target: 100% daily checks + ≥ 90% weekly preventive maintenance tasks completed

- Evidence: signed checklists + monthly maintenance audit

## Governance & Accountability Metrics (Prevents elite capture and disputes)

### Operating Charter Compliance

- Target: zero “off-book” transactions (no unreceipted payments) for 90 days

- Evidence: receipts, booking system, reconciliation reports

### Dispute Resolution Performance

- Target: ≥ 90% of grievances resolved within 7 days

- Evidence: grievance log with timestamps + outcomes

### Governance Discipline

- Target: Hub Management Committee meets monthly with:

  - minutes

  - financial summary review

  - downtime/maintenance report review

- Evidence: signed minutes + action tracker

## Data & IoT Metrics (Needed for operational proof + investor confidence)

### Data Completeness

- Target: ≥ 90% completeness across:

  - runtime

  - energy (kWh)

  - booking/throughput records

  - payments/receipts

- Evidence: monthly dashboard export + spot-checks

### Data Integrity (anti-fraud)

- Target: variance between:

  - recorded throughput vs runtime vs energy draw
stays within an agreed tolerance (e.g., ±10–15%)

- Evidence: audit comparisons

## Market & Value Chain Metrics (Commercial hub readiness)

### Market Pull / Offtake Proof

Scale-up requires at least one of:

- signed buyer agreement / offtake MoU

- repeat bulk buyers with documented purchase history

- processor sales growth trend (3-month increase)

### 16) Quality Standard Compliance

- Target: consistent quality specs (garri quality, hygiene, packaging) with ≤ 5% rejection/complaints

- Evidence: buyer feedback + QC log

## Inclusion & Social Metrics (Important because your baseline is male-heavy)

### Participation Targets (minimum inclusion triggers)

Because the farmer base is 34 male vs 7 female, scale-up should require:

- ≥ 25% of hub processing slots allocated to women/youth beneficiaries, or a clear step-up plan toward that

- At least 1 female in a financial-control role (cashier/admin/treasurer) or deputy role

- Evidence: booking records + committee roster

### Practical “Go/No-Go” Scale-Up Gate

Scale-up is activated when ALL conditions below are met:

- Repayment performance: On-time repayment ≥95% for 3 months; PAR30 ≤5%

- Collections threshold: ≥90% of expected monthly inflow (based on model totals above) for 3 months

- Operational reliability: uptime ≥90–95% and energy availability ≥95%

- Demand proof: utilization ≥60% for 8 weeks or waiting list ≥20% of slots weekly

- Governance proof: zero off-book transactions + grievances resolved within 7 days

- Data proof: ≥90% completeness and auditable logs

# Monitoring, Evaluation & Reporting (MER)

To ensure the effectiveness, efficiency, and sustainability of the PUE intervention in Akotogbo, a structured Monitoring, Evaluation, and Reporting (MER) framework will be deployed. This system will track energy usage, equipment performance, productivity outcomes, and community impact, while also integrating mechanisms for continuous feedback and improvement.

## Key Performance Indicators (KPIs)

| KPI Category | Indicator | Frequency |
| --- | --- | --- |
| Energy Utilization | kWh consumed per equipment category (daily/monthly) | Monthly |
|  | Peak load vs average load per site | Monthly |
| Operational | Machine uptime and downtime logs (hrs/month) | Weekly |
|  | Frequency of maintenance or repairs | Monthly |
|  | Processing rate and quantity | Daily |
| Economic Impact | Increase in monthly revenue per processor (₦) | Quarterly |
|  | Monthly fuel savings for e-mobility and agro-processors (₦) | Monthly |
| Social Impact | Number of jobs created (technicians, operators, riders) | Quarterly |
|  | Number of women/youths trained and engaged | Quarterly |
| Adoption | Number of active PUE users | Monthly |
|  | Number of cooperative members enrolled | Monthly |

Table 49:KPI

## Data Collection and Reporting Tools

A combination of digital tools and local record-keeping will be used to collect and transmit data reliably from field sites.

| Tool / System | Purpose | Managed By |
| --- | --- | --- |
| IoT Smart Meters | Track real-time energy consumption & machine uptime | Technical Partner / SPV |
| Mobile Enumerator Forms | Collect monthly performance and business data | PUE team |
| WhatsApp / SMS Survey Tools | Collect qualitative feedback from end-users | Various stakeholder |
| Equipment Logbooks | Record hours of use and faults | SPV |
| Digital Dashboard (central) | Aggregates all KPIs and generates automated reports | DI Team |

Table 50: Data Collection and Reporting Tools

Table 51: Feedback Loops

## Feedback Loops

| S/N | ITEM |  |  |  |
| --- | --- | --- | --- | --- |
| 1 | Operator Feedback Sessions | Operator and cooperative member | Monthly | discuss challenges, machine performance, and suggestions |
| 2 | Rider Survey Check-ins | E-mobility operators and association | Bi-Monthly | assess performance, route efficiency, battery swap satisfaction, and fuel savings. |
| 3 | Performance Alerts | All IOT enabled devices | Instant | flag high downtime, abnormal consumption, or device malfunctions to the technical team for prompt action. |
| 4 | Grievance Redress System | All beneficiaries | Instant | mobile-accessible form or WhatsApp hotline will allow users to submit complaints or service requests in real time. |
| 5 | Quarterly MEL Reports | Shared with stakeholders | Quaterly | key insights, deviations, and corrective actions. |

# Risk Assessment and Mitigation

Deploying Productive Use of Energy (PUE) infrastructure in Akotogbo presents several operational, financial, social, and institutional risks. This section outlines the key risks anticipated and the strategic mitigation measures integrated into the implementation design to ensure sustainability and long-term success.

## Risks Identified

| Risk Category | Description |
| --- | --- |
| Low Equipment Adoption | Users may be unwilling to switch from manual or diesel-powered methods due to habit or cost fears. |
| Machine Downtime | Equipment may break down frequently due to poor maintenance, improper use, or lack of spare parts. |
| Electricity Reliability | Mini-grid overload or poor solar sizing could affect equipment performance or user satisfaction. |
| Theft and Vandalism | Equipment, batteries, or solar panels may be stolen or damaged, especially at night or in isolated areas. |
| Lack of Operator Skills | Improper usage may cause damage or reduce equipment lifespan. |
| Financial Default | Operators may default on payment models (lease-to-own, usage fees, subscriptions). |
| Cooperative Failure | Poor management or conflicts can collapse cooperatives managing shared equipment. |
| Climate Disruptions | Heavy rains or flooding may affect logistics, deployment schedules, or equipment use. |
| Community Resistance | Resistance to cooperative models or shared infrastructure from individuals preferring personal ownership. |

Table 52: Risks Identified

## Mitigation Measures

| Risk | Mitigation Strategy |
| --- | --- |
| Low Equipment Adoption | • Community sensitization sessions before deployment • Early pilot demonstrations with lead users • Flexible financing (pay-as-you-use or lease-to-own) |
| Machine Downtime | • Operator and technician training prior to handover • Preventive maintenance schedules • Spare parts kits stored locally • Equipment logbooks for tracking faults |
| Electricity Reliability | • System design includes buffer for peak loads • Load staggering strategy • Battery banks and backup generation in hybrid systems |
| Theft and Vandalism | • Secure installation (anchor bolts, enclosures) • Community-led equipment protection committees • Consideration of asset insurance for high-value machines |
| Lack of Operator Skills | • Pre-deployment technical training • Step-by-step visual SOPs • On-call technical support system • Quarterly refresher training |
| Financial Default | • Equipment usage tied to cooperative performance • Usage monitoring via IoT (where applicable) • Group guarantees or staggered asset handover • Revenue-based repayment models |
| Cooperative Failure | • External facilitation and capacity-building support for 12 months • Strong bylaws and conflict resolution frameworks • Monthly governance reviews and advisory |
| Climate Disruptions | • Site selection considers drainage and elevation • Weather-resistant installations • Deployment flexibility during wet season |
| Community Resistance | • Choice between individual and cooperative models based on preference • Pilots to test both models • Transparent beneficiary selection criteria and inclusive engagement |

Table 53: Mitigation Measures

# Proposed Impact of the PUE on the Community

The implementation of Productive Use of Energy (PUE) infrastructure and equipment in Agadagba is projected to catalyze a range of socioeconomic, environmental, and institutional benefits. These impacts are both direct and indirect, addressing long-standing challenges in agro-processing, transportation, energy access, and rural livelihoods.

| Impact Area | Metric | Projected Outcome |
| --- | --- | --- |
| Processing Output | Tons/bags processed monthly | +250–350% increase |
| Average Processor Income | ₦ / month | +100–200% growth |
| E-Mobility Operators | Monthly Savings | ₦40,000–₦100,000 |
| Mini-grid Utilization | kWh / day increase | +400–500% |
| CO₂ Emission Reduction | Estimated % decrease | 25–40% |
| Employment | Jobs created | 120+ |
| Women Beneficiaries | % of total beneficiaries | Over 45% |

Table 54: Summary of Projected Outcomes by Year 1

The introduction of Productive Use of Energy (PUE) agro-processors in newly electrified rural communities offers a transformative opportunity to drive sustainable development, stimulate inclusive economic growth, and promote energy access. This PUE initiative aims to boost local productivity, empower rural livelihoods, encourage entrepreneurship, and enhance community resilience

## Contribution to the Sustainable Development Goals (SDGs)

The project directly contributes to several SDGs by integrating clean energy into productive rural enterprises. The electrification of agro-processing activities through mini-grids is expected to improve productivity, create decent jobs, and promote equitable economic participation.

| SDG | Goal Description | Project Contribution |
| --- | --- | --- |
| SDG 7 | Affordable and Clean Energy | Deployment of solar mini-grids and reduction in fossil fuel usage |
| SDG 8 | Decent Work and Economic Growth | Job creation and promotion of local agro-based industries |
| SDG 5 | Gender Equality | Inclusion of women in employment and entrepreneurial roles |

Table 55: Project Alignment with SDGs

# Challenges And Recommendations

The implementation of Productive Use of Energy (PUE) agro-processing systems in rural communities has faced a number of practical and strategic challenges. These issues have implications for both project design and execution, particularly around data accuracy, technical feasibility, and stakeholder coordination.

## Key Challenges

| Lesson Learned | Recommended Best Practice |
| --- | --- |
| Inexperience Enumerators from the enumerators database network | - Develop a tiered enumerator training program (digital LMS + practical field orientation). - Introduce supervisory layers where experienced enumerators review/validate submissions. - Deploy short competency tests before field deployment to ensure readiness. - Maintain a “gold pool” of certified enumerators for sensitive PUE projects. |
| Inconsistent Data Sources | - Establish a standardized data collection template with required fields and definitions. - Use triangulation (verify one data point from at least 2 independent sources). - Develop a data validation checklist before accepting field reports. - Centralize all data in a shared digital repository with version control. |
| Limited Literacy and Data Recording Among Processors | - Simplify questionnaires with visual aids (icons, diagrams, pictures). - Use assisted interviews instead of self-reporting. - Provide basic recordkeeping training for processors (use of tally sheets, pictorial logs). - Pilot digital record tools (voice-to-text apps, local language apps). |
| Delayed Responses from OEMs | - Prequalify and build a roster of responsive OEMs with service-level agreements (SLAs). - Use framework agreements that lock in response times. - Assign a dedicated vendor liaison officer for quicker escalation. - Introduce penalties or incentives tied to timely responses. |
| Partial Supplier Responses | - Issue structured Request for Quotation (RFQ) templates requiring detailed specifications. - Reject incomplete submissions and follow up with a second clarification round. - Establish preferred supplier partnerships for PUE equipment. - Require after-sales service commitments in all supplier responses. |
| Data Accuracy and Completeness | - Deploy real-time data collection tools (mobile apps with GPS + timestamp). - Automate data validation checks (e.g., flag outliers). - Require double-entry verification (two enumerators capture same site). - Conduct spot checks by project leads during enumeration. |
| Unrealistic delivery timeline | - Create a standard PUE project delivery timeline (benchmark based on past deployments). - Build buffer periods for procurement and logistics (typically 20–30% of total time). - Engage OEMs early to confirm realistic lead times before finalizing reports. - Use a Gantt chart planning tool to align activities and dependencies |

Table 56: Key Challenges and recommendations

## Forecasted Implementation Challenge

| Lesson Learned | Recommended Best Practice |
| --- | --- |
| Overloading of electric motors when using single-phase supply for machinery above 2–3 HP | Use three-phase power systems for all induction motors |
| Mini-grid disruption from startup surge currents | Equip all induction motor machines with variable speed drives or soft starters |
| Reliability of mini-grid power supply | Schedule PUE operations during peak solar generation hours (location-specific) |
| Insufficient mini-grid capacity for additional agro-processors | Coordinate with mini-grid developers to confirm grid compatibility and capacity before equipment deployment |
| Inconsistent year-round equipment use | Introduce smaller PUE appliances (e.g. wet milling machines, cold storage) to stabilise off-peak demand |
| Need for extension of mini-grid network to reach all processors | Reassess grid design with developers to incorporate provisions for PUE integration |
| Risk of equipment theft | Allocate security resources, especially for centralised agro hubs |

Table 57: Forecasted Implementation Challenge and recommendation

# Use of Artificial Intelligence (AI) in Report Development

In the preparation of this report, Artificial Intelligence (AI) was applied primarily as a language support and structuring tool. AI was used to improve the clarity, readability, and grammatical arrangement of the document to ensure that the information presented was coherent and professionally communicated.

It is important to emphasize that the substantive content of the report was not generated by AI. The data and insights were drawn from multiple reliable sources, including:

- Field Data: Primary information collected through surveys, assessments, and stakeholder engagements.

- Recommendations: Developed based on the experience and expertise of subject matter specialists.

- Budget Estimates: Sourced directly from Original Equipment Manufacturers (OEMs).

- Financial Models: Designed and validated by the financial team.

- Technical Inputs: Provided by the technical team with sector-specific knowledge.

AI therefore played a supporting role in enhancing the presentation of information, while the core knowledge, data, and analysis were derived from fieldwork, expert judgment, and technical and financial teams.